## Slide 1
2026
2027
Bifrost
Autonomus Navigation (Aerostack2)
(UPM)
Development Release
System
Embedding on Advanced Platform
(Yisus)
Event-Based Bifrost
(Fer, Gio)
Mechanical Development
(Salva)
Optics
(Nicola)
nSLAM (Yisus)
Today
23 days
May 4 - Jun 3
9 days
Jun 4 - Jun 17
11 days
Apr 22 - May 7
58 days
May 8 - Jul 29
6 days
Aug 13 - Aug 21
10 days
Sep 3 - Sep 16
43 days
Sep 17 - Nov 16
85 days
Jul 20 - Nov 16
22 days
Nov 16 - Dec 16
Jul 23
0 days
Oct 31
0 days
34 days
Apr 13 - May 31
65 days
Oct 1 - Dec 31
0 days
0 days
0 days
Apr
May
Jun
Jul
Aug
Sep
Oct
Nov
Dec
Jan
Bifrost Classical (IMX95)
Bifrost Classical (Orin)
Data Sampling
DoP & AoP Development
Integration
System On Board (RTK350)
Flights
Result Analysis (VO vs Polar)
Ex-Post
Tripod Holder Design Ready
Joselito (mecanizado)
QSLAM Gazebo Integr.
Joselito Sim Integration + ¿real flihgts?
Polarimetric Navigation
September 30, 2026
Neuromorphic Polarimetric Navigation
December 18, 2026
Autonomus Navigation (Simulator)
July 31, 2026
17 days
Apr 8 - May 1
Liquid Crystal Option Analysis
58 days
May 1 - Jul 22
D&D Rotatory System
44 days
Jun 1 - Jul 31
Fish Eye Design
31 days
Aug 1 - Sep 14
DFM Codesign
65 days
Sep 15 - Dec 15
Fish Eye Production
Autonomus Navigation (Real)
January 22, 2027
0 days
21 days
Aug 15 - Sep 14
LC Set Up
Jun 30
0 days
Dog Holder Design Ready
Aug 31
0 days
RTK Holder Design Ready (mecanizado)
nSLAM
October 15, 2026
0 days
38 days
May 1 - Jun 24
Algorithm Opti Dev (Gio)
22 days
Jul 15 - Aug 14
Tilt Sol.
31 days
Jul 20 - Aug 31
Terrestrial Test
19 days
Jun 4 - Jul 1
SLAM (IMX95)
22 days
Sep 15 - Oct 15
LC Lab Test
14 days
Oct 16 - Nov 5
LC Integration
16 days
Nov 5 - Nov 29
LC Field Test
Jun 25
0 days
Algo Optimization Failed
Jun 4
0 days
Bifrost IMX95 5 times slower than Orin
Jul 2
0 days
SLAM (IMX95) 20 - 25 fps
70 days
Jul 8 - Oct 14
Ultimate SLAM Adjustment
27 days
Jul 8 - Aug 14
nSLAM SOA
0 days
0 days
0 days
Nov 15
0 days
Dec 15
0 days
Project Re-Kickoff
Apr 8
System Flying
Sep 16
Ex-Post Release
Dec 15
Results Report
Ex-Post
Autonomus Navigation on Joselito (TRL8)
Dec 31
0 days
Optics Ready
Dec 15
0 days
System Working on Simulation
May 31
0 days
LC Feasible
Apr 30
0 days